## Sheet1
High Profile Report for November 2015
Project #, Applicant, Town and LUA | Project Description | Status
New Applications
P2015-167 Applicant: NYS Div. of Homeland Security Town: various LUA: various | Seven sites proposed for installation of meteorological monitoring stations "Mesonet sites". 814 project - new land use & development by a state agency. | Application received 10/5/15. Prior Pre-application file A2015-25 (initiated 4/2/15).
Permits/Determinations Issued
P2015-146 Applicant: Lyme Timber Town: Lake Pleasant, Hamilton Cty. LUA: Resource Management | The treatment area is located in the Perkins Clearing tract just north of Jessup River Road. The entire tract is 14,379 acres in size. The proposal involves even-aged management on 43 acres of timberlands. | Application received 8/27/15. Determined Complete 9/9/15. Presentation to Board 10/8/15. Permit issued 10/9/15.
P2015-130 Applicant: The Lyme Timber Company Town: Lake Luzerne, Warren Cty. LUA: Rural Use | Timber harvesting on a 121 acre portion of Lyme Timber's 3,630 acre Luzerne Tract. Treatments will include thinning, patch cuts, seed tree removal and shelterwood establishment to promote growth of healthy trees and establish new regeneration. | Application received 8/12/15 Determined Complete 9/2/15. Presentation to Board 10/8/15. Permit issued 10/9/15.
P2015-124 Applicant: MWF Adirondack, LLC Town: Colton, St Lawrence Cty. LUA: Resource Management | Shelterwood overstory removal harvest of 470± acres to release a well-established understory of approximately 8200 stems/acre, and enable the applicant to salvage value from a declining overstory, a jurisdictional harvest under the Agency's timber harvesting regulations. | Application received 8/6/15 Determined Complete 9/8/15. Presentation to Board 10/8/15. Permit issued 10/9/15.
P2015-22 Applicant: SBA Towers, Inc. Town: Lewis, Essex Cty. LUA: Low Intensity Use | Subdivision into sites by lease and a major public utility use involving installation of a new 65-foot tall monopine telecommunications tower (concealed as a simulated pine tree). Access to the facility will be an existing gravel driveway, and a new 574± foot long gravel drive. | Application received 2/10/15 Application Determined Complete 4/26/15. 90 day Clock extended. Permit issued 9/30/15.
Applications Determined Complete
P2015-137 Applicant: ARISE Town: Tupper Lake, Franklin Cty LUA: Moderate Intensity Use & Resource Management | Temporary re-use of an existing ski facility; previously permitted by prior Agency permits. The facility will primarily operate from 9am to 4pm Fridays through Sundays and holidays; no snowmaking or nighttime skiing is proposed. | Application received 8/21/15 Determined Complete 9/2/15. 60 day clock 11/1/15. 90 day clock 12/1/15.
Notices of Incomplete Permit Applications (NIPA)
P2015-159 Applicant: Fawn Ridge, LLC Town: North Elba, Essex Cty. LUA: Moderate Intensity Use, Rural Use, Hamlet | "Trailside at Fawn Ridge," a proposed 43-lot subdivision creating 40 new single family dwelling building lots, ranging in size from approximately 1± acre to 7± acres. Of the 40 proposed building lots, 34 are classified Moderate Intensity Use area on the Adirondack Park Land Use and Development Plan Map, and 6 are classified Rural Use. The proposed 34 Moderate Intensity Use lots will connect to the municipal wastewater system and the 6 proposed Rural Use area lots will have on-site wastewater treatment systems. | Application received 9/21/15. NIPA issued 10/16/15.
P2015-154 Applicant: Town of Indian Lake Town: Indian Lake, Hamilton Cty. LUA: Rural Use | Repairs and replacement of elements of Lake Abanakee Dam including: replace sluice gate, replace flash boards with concrete spillway crest, addition of retaining walls and bank material armor shoreline, add concrete mass behind spillway. | Application received 9/14/15. NIPA issued 9/29/15.
P2014-108 Applicant: Lake Flower Lodging, LLC Town: North Elba, Essex Cty. LUA: Hamlet | Remove three existing hotel structures and re-develop the site with a new 93 room four story hotel approximately 92,711 sq. ft. in footprint. The hotel will include: restaurants; bar; conference/meeting facilities; indoor/outdoor spa; and an open deck/dock area, a portion of which will be semi-public. A portion of the proposed structure, is located within 50 ft. of the MHWM of Lake Flower and requires a variance. The project will also require permits due to wetland impacts and the height >40'. | Application received 7/11/14. Letter dated 7/17/14 extends review clock pending a more complete submission from applicant. Coordination with local government and other regulatory agencies continues. Formerly Pre-application A2013-128.
P2015-17 Applicant: New Cingular Wireless PCS, LLC (AT&T) Town: Queensbury, Warren Cty. LUA: Moderate Intensity | Subdivision into sites by lease and a major public utility use involving installation of a new 130 foot tall monopole telecommunications tower with related antennas & equipment shelter. | Application received 2/3/15 NIPA issued 2/18/15. No additional information yet received.
P2014-226 Applicant: St. Lawrence Seaway RSA Cellular Partnership d/b/a Verizon Wireless Town: Fine, St. Lawrence Cty. LUA: Resource Management | Lease a 100 foot by 100 foot (0.23± acre) parcel to St. Lawrence Seaway RSA Cellular Partnership (dba Verizon Wireless) for the construction and operation of an 80 foot tall monopole telecommunications tower and a 12 foot by 30 foot equipment building. | Application received 12/24/14. NIPA issued 1/15/15. 2nd NIPA issued 10/8/15.
P2014-108 Applicant: Lake Flower Lodging, LLC Town: North Elba, Essex Cty LUA: Hamlet | Remove three existing hotel structures and re-develop the site with a new 93 room four story hotel approximately 92,711 sq. ft. in footprint. The hotel will include: restaurants; bar; conference/meeting facilities; indoor/outdoor spa; and an open deck/dock area, a portion of which will be semi-public. A portion of the proposed structure, is located within 50 ft. of the MHWM of Lake Flower and requires a variance. The project will also require permits due to wetland impacts and the height of the structure >40'. | Application received 7/11/14. Letter dated 7/17/14 extends review clock pending a more complete submission from applicant. Coordination with local government and other regulatory agencies continues. Formerly Pre-application A2013-128.
P2015-107 Applicant: New Cingular Wireless Town: Chester, Warren Cty. LUA: Resource Management | GP2010G-1 for installation of a new 70-foot-tall monopole telecommunications tower at an Agency approved site on Panther Mountain (i.e., a horizontal co-location). All existing AT&T antennas (and supporting equipment) will be removed from the existing 68-foot-tall guyed tower that is also on site. | Application received 7/7/15 NIPAs issued 7/17/15 and 8/24/15.
Variance Applications
P2014-53 Applicant: L S Marina LLC Town: Harrietstown, Franklin Cty. LUA: Hamlet | Variances requested from the Shoreline setback for the construction of new covered floating docks, which do not meet the Adirondack Park Agency Regulatory definition of a "boathouse" (and therefore are not exempt from the shoreline setback restrictions). | Pre-application file A2013-197 initiated 12/10/13; resulting from JIF. Application received 4/15/14. Request for Additional Info. (RFAI) issued 5/2/14 and 7/30/14. Additional Agency correspondence issued 12/22/14, and 6/26/15.
P2015-73 Applicant: Mahoney Town: Corinth, Saratoga Cty. LUA: Low Intensity, Rural Use | Construction of a single family dwelling on an exisitng lot having less than 100 feet of width within the shoreline setback area, (i.e. within 75 feet of the mean high water mark of Hunt Lake). Parcel boundaries in existence with no viable alternative for adjusting lot lines. A shoreline lot width variance is required. | Received 5/8/15. RFAI issued 5/20/15, 8/3/15, and 9/25/15. Additional info. received 10/13/15. Recommend for delegation to DDRP
P2014-90 Applicant: Kailyn Realty II, LLC. Town: North Elba, Essex Cty. LUA: Moderate Intensity | Variance application to vary the 806 shoreline setback requirement to allow replacement and expansion of a pre-existing, single story boathouse and dock with a new structure over 1,200 square feet in size that has second story living space which is not for the storage of boats or equipment. | Application received 6/9/14. RFAI issued 6/25/14. Additional information received 1/9/15. 2nd RFAI issued 3/20/15. Hearing conducted 6/22/15.
P2015-62 Applicant: Peter Day Town: Vill of Lake Placid, North Elba, Essex Cty. LUA: Hamlet | Variance request to add a lakeside covered deck and patio onto a pre-existing structure located within the 50 foot shoreline setback. | Application received 4/23/15 RFAI issued 5/8/15
P2015-113 Applicant: Adkins Town: Inlet, Hamilton Cty. LUA: Rural Use | Requesting a variance from the shoreline lot width restrictions for the construction of a single family dwelling with on-site wastewater treatment system on a Rural Use area lot that has less than 150 feet of shoreline on Limekiln Lake. | Application received 7/20/15. RFAI issued 8/4/15.
P2015-160 Applicant: Willette, Town: St. Armand, Essex Cty. LUA: Rural Use | Requesting a variance from the river area shoreline setback for construction of a retaining wall. | Application received 9/23/15.
P2015-177 Applicant: Windle Town:Putnam; Washington Cty. LUA: Low Intensity Use | Requesting a variance from the shoreline setback to replace and expand a single family dwelling. | Application received 10/27/15. NEW APPLICATION
Pre-Applications
A2015-91 Applicant: Francato Town: Fort Ann, Washington Cty. LUA: Low Intensity Use | Variance request for shoreline lot width. Construction of single family dwelling on post-1973 subdivision lot with less than 125 feet fo shoreline. | Pre-application file initiated 10/19/15.
A2015-73 Applicant: Mitrowitz Town: Harrietstown, Franklin Cty. LUA: Moderate Intensity Use | Requesting a variance from the shoreline setback for construction of an elevator stairway to the shoreline. | Pre-application file initiated 8/10/15.
A2015-65 Applicant: Warren Cty Sheriff's Office Town: Warrensburg, Warren Cty. LUA: Moderate Intensity Use | Construction of a 60 foot tall telecommunications tower for emergency services. | Pre-application file initiated 7/21/1. Pre-application meeting 8/4/15.
A2015-66 Applicant: Town of Warrensburg Town: Warrensburg, Warren Cty. LUA: Low Intensity Use | Variance request to construct a pavilion(600 square feet), and observation deck(10 x 12) within 150 of mean high water mark of Recreational River. | Pre-application file initiated 7/23/15.
A2015-52 Applicant: NTPA Town: Diana LUA: various | New York Power Authority (NYPA) is proposing to rebuild 85 miles of a 230 Kv double circuit line in northern New York. Approximately 2 miles of the project are located within the Adirondack Park. Preliminary structure recommendations involve replacing two H-frame structures carrying two circuits within the right-of-way that are approximately 70 feet tall each with one double circuit steel monopole structure approximately 105 feet in height that will carry two circuits. Upgrades to 1.5 miles of large utility line in town of Diana. | Pre-application file initiated 6/17/15. Agency staff providing advisory comments in an Article 7 review.
A2015-55 Applicant: NYSEG Town: Saranac Clinton Cty LUA:Rural, Moderate, & Low Intensity Use | Major utility line upgrade - replacement of 46 foot poles with 65 foot poles. | Pre-application file initiated 6/22/15.
A2015-44 Applicant: Rockwell Town: Inlet, Hamilton Cty. LUA: Rural Use | Variance request for wastewater treatment system within 100 feet of MHWM of Limekiln Lake. | Pre-application file initiated 5/28/15.
Pre-Applications
A2015-42 Applicant: Stephan Town: Essex, Essex Cty. LUA: Hamlet | Variance request to convert barn with setback into single family dwelling or guest cottage. | Pre-application file initiated 5/29/15.
A2015-40 Applicant: Davideau Town: Dresden, Washington Cty. LUA: Moderate Intensity | Variance request replace and expand single family dwelling located with shoreline setback | Pre-application file initiated 5/22/15.
A2015-39 Applicant: Purdy, Don Town: Arietta, Hamilton Cty. LUA: Rural, Low & Moderate Intensity use | County's Emergency Services Tower - near Piseco Lake. | Pre-application meeting 6/2/15.